## schedule
[6 empty] | 2024-02-12 |  |  |  |  | 2024-02-19 |  |  |  |  | 2024-02-26 |  |  |  |  | 2024-03-04 |  |  |  |  | 2024-03-11 |  |  |  |  | 2024-03-18 |  |  |  |  | 2024-03-25 |  |  |  |  | 2024-04-01 |  |  |  |  | 2024-04-08 |  |  |  |  | 2024-04-15
Task ID | Task Title | Task Owner | Start Date | Due Date | % Complete | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10
[6 empty] | M | T | W | T* | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T* | F | M | T | W | T | F | M | T | W | T* | F | M | T | W | T | F | M | T | W | T* | F | M | T | W | T* | F
1 | Project Conception and Initialization |  |  |  | 100%
1.1 | Initial Research |  |  |  | 100% | bar: Week 1 M to Week 1 T*
1.2 | High-Level System Definition |  |  |  | 100% | bar: Week 1 T to Week 1 T*
1.3 | Requirements Definition |  |  |  | 100% | bar: Week 1 W to Week 1 T*
1.4 | Kick-Off Presentation |  |  |  | 100% | bar: Week 1 T*
2 | System Design and Modeling |  |  |  | 67.5%
2.1 | Research System Design |  |  |  | 80% | bar: Week 2 M to Week 5 T*
2.2 | Design Physical System |  |  |  | 90% | bar: Week 3 M to Week 3 F
2.3 | MATLAB Physical System Model |  |  |  | 75% | bar: Week 4 M to Week 4 F
2.4 | MATLAB Control System Model |  |  |  | 25% | bar: Week 5 M to Week 5 T*
3 | Implementation |  |  |  | 55%
3.1 | Procure Physical Components |  |  |  | 100% | bar: Week 4 M to Week 5 T*
3.2 | Physical Component Integration |  |  |  | 80% | bar: Week 4 T to Week 5 T*
3.3 | Software Implementation |  |  |  | 20% | bar: Week 5 M to Week 5 T*
3.4 | Hardware/Software Integration |  |  |  | 20% | bar: Week 5 T to Week 5 T*
4 | Verification |  |  |  | 0%
4.1 | Unit Testing |  |  |  | 0%
4.2 | Integration Testing |  |  |  | 0%
4.3 | Functional Testing |  |  |  | 0%
4.4 | System Level Testing |  |  |  | 0%

## budget
Item | Quantity | Price/ea
Arduino Uno | 1 | 0
DC Brushless Motor | 4 | 0
Electronic Speed Controller | 4 | 0
Battery | 1 | 0
Drone Chassis | 1 | 0
IMU | 1 | 0
RC Receiver/Transmitter | 1 | 55
Protoboard Shield | 1 | 0
Hook-up Wire | 5 | 0
| Total: | 55